## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/05 - 09/12 | Picked group name Picked project description Chose important requirements/features Set up Github/Jira | Figuring out Github Desktop | None | Weekly Meetings Using Jira for user stories Communciation | 0 | 0 | 0 | 0 | 0 | 8 | ~4.5 | 3 | ~1 | ~3 | 0 | 0 | 0 | 3 | ~.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## ahnafTajwar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 7.5 | 4.5 | 3 | 0 - learned how to use Git Desktop 1 - Worked on the SPPP document for Non-functional requirements 5 - Discussed plans and updates with team on Discord and Zoom 6 - Setup IDE and Github 7 - Prepared presentation | 1 | 2 | 0 | 0 | 0 | 3 | 0.5 | 1 | 1. Write Non-functional requirements section of SPPP 2. Set up git, commit introduction on git 3. Completed Technical Competence part of Risk Assessment 4. Participate in Iteration 0 presentation 5. Lab 1 | None | None | 0 - Learn Flask, React, and Jira 1 - Figure out more concrete security requirements 3 - Test out a basic application with python and flask 5 - Meet with team for individual updates 7 - Prepare next presentation | 10

## lazaroPerez
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Quality Assurance
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 8 | 6 | 1 | 0 - researched Jira and made comparison to Pivotal Tracker 1- Workerd on the SPPP document for Summary and QA Sections 5 - Had discussions with team members on discord channel. | 2 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 1. Write 3 sections of SPPP 2. Set up GitHub Desktop, checked out the Lab1 branch and added a brief about myself. Then committed and pushed the change to the origin remote Repository | 1. Figuring out how to change the branch and checkout into the branch | Was able to figure out how to merge the additions into the lab1 branch | 1 - Setup Development Environment for the Back end Database as well as the functionality of the database and the website. | 10

## samanthaMathis
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 8 | 5 | 3 | 0 - learn git desktop 1 - define high level requirements, Risk Managements 5 - make project plan, send reminders to team members 6 - set up git 7 - prepare presentation | 1 | 1.5 | 0 | 0 | 0 | 3 | 0.5 | 2 | SPP (Management Plan) Risk Management Spreadsheet Slideshow Presentation Lab1 Commit | None | None | Set Up Jira and add User stories Set up Database Skeleton of a website Demo Video and presentation SDD document | 2023-10-15

## saahilVashishta
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/04/2023 - 09/12/2023 |  |  |  | 0 - Figure out Git 1 - define high level Functional requirements 1 - define Related work 6 - set up git and Flask 7 - prepare presentation | 2 | 4 |  |  |  |  | 0.5 | 0.5 | 1. Write Essential Functional Requirements 2. Write Desirable Functional Requirements 3. Write Optional Functional Requirements 4. Define related work 5. Complete Requirements part for the presentation as the requirement leader 6. Created Team logo 7. Lab 1 commit | 1. Not able to connect Github desktop to the repo | 1. Solved- Needed to sign out and sign in again out of Git on Mac

## Shajee Ur Rehman
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/04/2023 - 09/12/2023 | 4.75 |  |  | 0 - Learn how to setup Git Desktop 0 – Connect Git with VS Code 1 – Added essential, desireable and optional features to the SPPP 5 – communicated to team members about joining late 5 – Discuss with team members on channel and got up to speed 6 – Discuss with Team about if we use Jira or Pivotal, and dev environment 7 – Contribute to group presentation | 1 | 2 | 0 | 0 | 0 | 1.25 | 0.5 | 0 | Added more Potential features to the project in SPPP Work on Current presentation | none | none | Added more Potential features to the project in SPPP Learn Flask, React, and Jira Figure out more concrete security requirements Get familiar with using python and flask Meet with team for individual updates Work on next presentation | 10

## jianSong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Architecture and Design Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 7 | 6 | 3 | 0 - learn git desktop 1 - Workerd on the SPPP document 5 - Discussed general plans with team on Discord and Zoom and made sure everyone knows his responsibility 6 - set up IDE and Git, Determined additional tools to use 7 - prepare presentation slides and video | 1 | 2 | 0 | 0 | 0 | 3 | 1 | 1 | SPPP Related Work & Configuration; Risk Management Spreadsheet; Slideshow Presentation; Decided by the team - Jira for progress tracking; Lucid Chart for UML diagrams; Postman for API testing; Use Github Flow branching strategy; Lab1 Commit. | Not familiar with Github Desktop version | Took a little time to get myself familirized | 0 - learn Flask 2 - draft an overall architecture design for our app; start drafting SDD documents 3 - finish starter code for the app 5 - maintain ongoing attendence of team meetings | 10